## Risk Log
Risk Identification and Description | [6 empty] | Risk Assessment |  |  |  |  | Risk Response
ID | Category | Risk Name | Risk Description & Details | Status | Identified By | Identification Date | Likelihood | Impact | Risk Level (L*I) | Risk Owner | Escalation | Risk Response Strategy | Action Details (effort & responsible) | Target Date | Traceability/Comments
RL01 | Data Protection | Pierdere date utilizatori | Din cauza lipsei unui backup fizic propriu al bazei de date Firestore, exista riscul pierderii permanente a datelor utilizatorilor în caz de stergere accidentala sau compromitere a contului Firebase, ceea ce ar duce la pierderea irecuperabila a istoricului de antrenamente si nutritie. | Approved | Balanoiu Nicolae Andrei | 01/10/2025 | 2 | 5 | 10 | Balanoiu Nicolae Andrei | No | Reduce | Firebase Firestore backup automat activat. Regulile Firestore Security Rules restrictioneaza accesul la datele unui utilizator exclusiv prin autentificarea proprie. | 22/06/2026 | R1 (Project Charter)
RL02 | External Dependency | Indisponibilitate API nutritional extern | Din cauza dependentei de API-uri externe (USDA FoodData Central, Open Food Facts, Nutritionix) pentru datele nutritionale, exista riscul ca acestea sa devina temporar sau permanent indisponibile, ceea ce ar duce la imposibilitatea cautarii alimentelor si a scanarii codurilor de bare în aplicatie. | Approved | Balanoiu Nicolae Andrei | 01/10/2025 | 3 | 4 | 12 | Balanoiu Nicolae Andrei | No | Reduce | Implementarea unei baze de date interne Firestore cu produse alimentare adaugate de utilizatori (customProductService). Utilizarea mai multor API-uri ca fallback (USDA + Open Food Facts + Nutritionix). | 22/06/2026 | R4 (Project Charter); R-01 (Status Report); REQ-004, REQ-008
RL03 | Staffing | Dependenta de un singur developer | Din cauza faptului ca proiectul este dezvoltat de o singura persoana, exista riscul ca orice indisponibilitate (boala, urgente) sa blocheze complet progresul, ceea ce ar duce la întârzieri sau livrare incompleta a functionalitatilor planificate. | Approved | Balanoiu Nicolae Andrei | 01/10/2025 | 2 | 4 | 8 | Balanoiu Nicolae Andrei | No | Accept | Mentinerea unei documentatii tehnice detaliate (ARCHITECTURE.md, API_REFERENCE.md, cod comentat pe GitHub) pentru a facilita continuarea proiectului în orice situatie. | 22/06/2026 | R-02 (Status Report)
RL04 | Business | Concurenta puternica din piata de fitness | Din cauza existentei unor competitori cu resurse semnificative (MyFitnessPal, Hevy, Strong, Cronometer), exista riscul ca aplicatia sa nu atraga utilizatori suficienti, ceea ce ar duce la un impact redus pe piata si la imposibilitatea monetizarii sau atragerii de investitori. | Approved | Balanoiu Nicolae Andrei | 01/10/2025 | 3 | 3 | 9 | Balanoiu Nicolae Andrei | No | Accept | Monitorizarea periodica a pietei de fitness. Diferentierea prin planuri de antrenament pe cicluri configurabile si integrarea completa workout + nutritie într-o singura platforma. | 22/06/2026 | R6 (Project Charter); R-03 (Status Report)
RL05 | IT Security | Vulnerabilitati de securitate în comunicarea cu API-urile externe | Din cauza utilizarii unor API-uri externe si a transmiterii datelor utilizatorilor prin retele publice, exista riscul expunerii datelor sensibile sau al atacurilor de tip injection/interception, ceea ce ar duce la compromiterea securitatii conturilor utilizatorilor. | Approved | Balanoiu Nicolae Andrei | 01/10/2025 | 2 | 4 | 8 | Balanoiu Nicolae Andrei | No | Reduce | Utilizarea exclusiva a HTTPS pentru toate request-urile externe. Firestore Security Rules limiteaza accesul la date per utilizator autentificat. Validarea si sanitizarea input-urilor utilizatorilor. | 22/06/2026 | R8 (Project Charter)
RL06 | Technical | Instabilitate framework AI pentru import plan antrenament | Din cauza utilizarii unui framework AI pentru parsarea si importul planurilor de antrenament din fisiere multi-format (xlsx, txt, pdf), exista riscul ca acesta sa fie instabil sau sa produca rezultate impredictibile, ceea ce ar duce la esuarea importului sau generarea unor planuri de antrenament incorecte. | Approved | Balanoiu Nicolae Andrei | 01/10/2025 | 2 | 3 | 6 | Balanoiu Nicolae Andrei | No | Reduce | Testare extinsa a functionalitatii AI înainte de integrare. Implementarea unui fallback manual pentru import (utilizatorul poate introduce datele manual sau folosi template Excel standard). | 22/06/2026 | R7 (Project Charter); REQ-012
RL07 | Business | Recenzii negative cauzate de bug-uri nerezolvate | Din cauza prezentei unor bug-uri active (ex: dublarea macronutrientilor si kcal la alimentele scanate - I-01; calendar nutritional neresponsiv - I-02), exista riscul primirii unor recenzii negative, ceea ce ar duce la scaderea numarului de descarcari si afectarea imaginii produsului pe piata. | Approved | Balanoiu Nicolae Andrei | 01/10/2025 | 3 | 3 | 9 | Balanoiu Nicolae Andrei | No | Reduce | Quality testing manual si unit tests automate înainte de fiecare release. Remedierea bug-urilor prioritare (I-01: macronutrienti x2, I-02: calendar responsiv) înainte de lansarea finala. Backlog Trello monitorizat activ. | 22/06/2026 | R3 (Project Charter); I-01, I-02 (Status Report); Trello: 'Macronutrients and kcal x2', 'Fix Responsive Nutrition Calendar'
Note on B2: The risk identifier. It should be numbered sequentially.
Note on C2: Categories of risks related to the area affected by the risk (e.g. Business, IT, People & Organisation, External and Legal, Sustainability, Data Protection, IT Security>
Note on D2: A short title for the risk.
Note on E2: A description of the risk that may occur in the project and its causes. What kind of problems will the risk result in and risk dependencies. A structured formulation of the opportunity or threat in the form of (route) Cause – Risk –Effect, along with potential risk inter-dependencies.
Note on F2: The risk status can be any of the following: Proposed: This is the initial status. Use this while the risk is still being specified. Assessing: Use this status to initiate an assessment. Waiting for Approval: Use this to request approval. Before applying this status, make sure the assessment is complete and the estimates are reliable. Approved: This status is set once the risk possibility has been accepted. Rejected: This status is set if the risk was rejected as not relevant. Closed: This status is set once the risk has been managed (e.g. mitigation )
Note on G2: The person who identifies the risk.
Note on H2: The date when the risk was identified.
Note on I2: A numeric value denoting the estimate of the probability that the risk will occur. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on J2: A numeric value denoting the severity of the impact of the risk (should it occur). The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on K2: The risk level is the product of the likelihood and impact (RL=L*I).
Note on L2: The person accountable for the management and monitoring of this risk.
Note on M2: To be escalated to the Directing or Steering Layers: Yes or No.
Note on N2: The available strategies to deal with the identified risks are: - Avoid: risk avoidance, working the project or project plan around those conditions or activities which introduce the risk; - Reduce: risk mitigation or reduction through the proactive implementation of risk reduction activities; - Accept: acceptance of the risk. In this cases, contingency plans can also be defined in case the risk occurs; - Transfer/Share: transfer or share a risk with other entities, e.g. through insurances, sub-contracting etc.
Note on O2: Description of the action: objective of the action, scope, deliverables, person responsible and effort estimates.
Note on P2: The date that the action is expected to be implemented.
Note on Q2: The ID(s) of the task (in the Project Work Plan) implementing the risk actions, or/and the IDs of related change, issue or decisions log entries. Any additional information related to the risk approval (e.g. date) or related to the risk actions (activities).