## Issue Log
Issue Identification and Description | [6 empty] | Issue Assessment and Action Description
ID | Category | Title | Description | Status | Identified By | Identification Date | Action Details (effort & responsible) | Urgency | Impact | Size | Target Date | Issue Owner | Escalation | Traceability/Comments
IL-01 | Tehnic | Macronutrienti si kcal x2 pentru aplimente | macronutrientii si kcal sunt dublate fata de valorile reale returnate de API | Open | SANDRA-ANDREEA CORMOS | 2026-06-02 | Investigarea logicii de parsare si corectare a clacului macronutrientilor - Balanoiu Nicolae Andrei | 5 | 5 | 3 | 2026-06-22 | Balanoiu Nicolae Andrei | No | RL02 (Risk Log); R-01 (Status Report); REQ-004, REQ-008; Trello: 'Macronutrients and kcal x2 for Scanned Foods'
IL-02 | UX | Calendar nutritional - afisare incorecta pe anumite dimensiuni de ecran | Calendarul nutritional nu se afiseaza corect pe dispozitive cu dimensiuni de ecran diferite fata de dimensiunea standard de testare. Layout-ul se suprapune sau elementele sunt trunchiate. | Open | SANDRA-ANDREEA CORMOS | 2026-06-02 | Revizuirea stilurilor responsive si testarea pe multiple dimensiuni de ecran - Balanoiu Nicolae Andrei | 3 | 3 | 2 | 2026-06-22 | Balanoiu Nicolae Andrei | No | RL07 (Risk Log); I-02 (Status Report); Trello: 'Fix Responsive Nutrition Calendar'
IL-03 | UX | Imaginile produselor nu se afiseaza in lista de cautare | La cautarea unui aliment dupa nume sau cod de bare, imaginea produsului nu se afiseaza in rezultatele listei. Campul de imagine este gol | Open | FELIX | 2026-06-01 | Verificarea endpoint-ului de imagini din API si corectarea logicii de afisare - Balanoiu Nicolae Andrei | 2 | 2 | 1 | 2026-06-22 | Balanoiu Nicolae Andrei | No | I-03 (Status Report); Trello: 'Food Images in Search'
Note on C3: The issue identifier. It should be numbered sequentially.
Note on D3: Categories of issues related to the area affected by the issue (e.g. Business, IT, People & Organisation, External and Legal, Sustainability, Data Protection, IT Security, UX).
Note on E3: Short name for (describing) the issue.
Note on F3: A description of the issue and consequences of doing nothing.
Note on G3: The issue status can be any of the following: Open: the issue has been identified but no decision yet on how to resolve it. Postponed: this status is set for postponing the issue due to other priorities. Resolved: this status indicates that all necessary actions are completed and the issue is resolved. Closed: this status indicates the closing of the issue once the work is completed and verified.
Note on H3: The name of the person who identifies the issue.
Note on I3: The date that the issue has been raised.
Note on J3: Description of the recommended action, steps, deliverables, timescale, resources and effort involved.
Note on K3: A numeric value denoting the urgency of the issue. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on L3: A numeric value denoting the severity / impact of the issue. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on M3: Issue size represents the effort related to the issue resolution. The possible values are: 5=Very high 4=High 3=Medium 2=Low 1=Very low
Note on N3: The date that the issue is expected to be resolved.
Note on O3: The person accountable for the effective issue resolution.
Note on P3: To be escalated to the Directing or Steering Layers: Yes or No.
Note on Q3: The ID(s) of the task (in the Project Work Plan) implementing the issue actions, or/and the IDs of related change, risk or decisions log entries. Any additional information related to the issue actions (e.g. activities, approvals).